## Report
LOGO | [5 empty] | Product Owner: Clark Campbell | [11 empty] | Project: Corner Stone - Front Office | [25 empty] | Report Date: Week 21
[6 empty] | Scrum Master: Larry Elkins | [11 empty] | Vision: Upgrade Sales Configuration System | [25 empty] | Project Duration: Jan 01 13 - Jun 22 13
Business Objectives |  |  |  |  | Feature Sets |  |  |  |  | Releases and Sprints | [8 empty] | Schedule | [24 empty] | 7-Key Status
˜ | ˜ | ˜ | ˜ |  | ˜ | ˜ |  |  |  | Release 1 |  | Order Design and Pricing Configuration | [6 empty] | ˜ | ˜ | ˜ | ˜ | ˜ | ˜ | ˜ | ˜
| ˜ |  |  |  |  | ˜ |  |  |  |  | Sprint 1 | [7 empty] | ˜ | ˜
| ˜ | ˜ | ˜ |  | ˜ | [5 empty] | Sprint 2 | [9 empty] | ˜ | ˜
˜ |  |  |  |  | ˜ | [5 empty] | Sprint 3 | [11 empty] | ˜ | ˜
[6 empty] | ˜ |  |  |  |  | Sprint 4 | [13 empty] | ˜ | ˜
| ˜ | ˜ | ˜ | ˜ |  |  | ˜ | ˜ |  | Release 2 |  | Availability-to-Promise & Brochure Displays | [14 empty] | ˜ | ˜ | ˜ | ˜ | ˜ | ˜ | ˜ | ˜
| ˜ | [5 empty] | ˜ |  |  |  | Sprint 5 | [15 empty] | ˜ | ˜
| ˜ | ˜ |  | ˜ |  |  | ˜ |  |  |  | Sprint 6 | [17 empty] | ˜ | ˜
| ˜ | [6 empty] | ˜ |  |  | Sprint 7 | [19 empty] | ˜ | ˜
|  |  | ˜ |  |  |  |  | ˜ |  |  | Sprint 8 | [21 empty] | ˜ | ˜
|  | ˜ | ˜ | ™ |  |  |  |  | ™ | Release 3 |  | Paper and Online Invoicing | [22 empty] | ˜ | ˜ | ˜ | ˜ | ˜ | ™ | ™ | ™
[9 empty] | ˜ |  | Sprint 9 | [23 empty] | ˜ | ˜
|  | ˜ | ˜ | [5 empty] | ˜ |  | Sprint 10 | [25 empty] | ˜ | ˜
|  |  |  | ™ |  |  |  |  | ™ |  | Sprint 11 | [27 empty] | ™ | ™
[9 empty] | ™ |  | Sprint 12 | [29 empty] | ™ | ™
| ™ | ™ |  |  |  | ™ | ™ | ™ |  | Release 4 |  | Final Bug Clean-up | [30 empty] | ™
| ™ | ™ |  |  |  | ™ | ™ | ™ |  |  | Sprint 13 | [31 empty] | ™
Risks, Qualitative, Other Metrics
˜ |  | ™ |  |  | ˜ | ˜ | ˜ |  |  | A | Major Risk - Capacity of Purchased Software | [32 empty] | Stake Holders | Business Benefits | Work Schedule | Scope | Team | Risk | Organizational Benefits
| ™ |  | ˜ | ˜ |  |  |  | ˜ | ˜ | B | Minor Risk - Losing Key Developer From the Team
|  |  | ™ | ™ |  | ™ | ™ | ™ | ™ | C | Robust Interfaces with Remaining Legacy Systems
™ | ™ | ™ | ™ | ™ | ˜ | ˜ | ˜ | ˜ | ™ | D | Client and Sales Team Satisfaction
Key Metrics
Earn community appreciation | Inspire customers for a better product | Building Complete | Systems Operational | People Deployed | Upgrade Order Design Features | Upgrade Pricing Features | Upgrade Available-to-Promise Features | Upgrade Brochure Display Features | Upgrade Invoicing Features | A | Leakage (Wdef/MM) | [7 empty] | 0.35 | 0.3 | 0.29 | 0.31 | 0.42 | 0.43 | 0.39 | 0.38 | 0.34 | 0.29 | 0.29 | 0.31 | 0.37 | 0.45 | 0.38 | 0.38 | 0.31 | 0.37 | 0.49 | 0.39 | 0.4
[10 empty] | B | Defect Rate (Wdef/MM) | [7 empty] | 25 | 22 | 23 | 24 | 21 | 29 | 28 | 32 | 15 | 20 | 20 | 35 | 28 | 27.6 | 38 | 39 | 21 | 22 | 27.6 | 28 | 31
[10 empty] | C | Timeliness (%) | [7 empty] | 99% | 99% | 95% | 96% | 95% | 78% | 77% | 51% | 72% | 76% | 97% | 96% | 95% | 95% | 45% | 49% | 96% | 95% | 95% | 77% | 39%
[10 empty] | D | Effort Efficiency (%) | [7 empty] | 95% | 85% | 96% | 81% | 83% | 81% | 81% | 81% | 96% | 85% | 99% | 82% | 82% | 75% | 73% | 72% | 82% | 82% | 81% | 81% | 45%
[10 empty] | E | Correction Cost (%) | [7 empty] | 5.6% | 6.6% | 6% | 6.7% | 5.2% | 5.1% | 7.2% | 7.3% | 5% | 6.4% | 6% | 6.8% | 5% | 8.1% | 8.2% | 8.6% | 6.8% | 5.3% | 5.1% | 5.6% | 7.2%
[10 empty] | F | Productivity (%) | [7 empty] | 96% | 87% | 96% | 84% | 98% | 97% | 96% | 77% | 76% | 74% | 73% | 83% | 99% | 98% | 96% | 77% | 85% | 91% | 92% | 93% | 78%
[10 empty] | # People on the Development Team: | [8 empty] | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
[10 empty] | Average Weekly Team Velocity: | [8 empty] | 35 | 35 | 36 | 36 | 36 | 37 | 38 | 39 | 38 | 34 | 35 | 30 | 29 | 35 | 34 | 34 | 36 | 37 | 38 | 40 | 41 | 40 | 40 | 39 | 42
[19 empty] | Week 01 | Week 02 | Week 02 | Week 04 | Week 05 | Week 06 | Week 07 | Week 08 | Week 09 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 |  | Complete |  |  | ˜
[13 empty] | Releases, Sprints, Metrics | [31 empty] | Incomplete |  |  | ™
[15 empty] | & Risks | [29 empty] | Backlog
Adequate
[16 empty] | Sprint Dates | [28 empty] | Worrisome
[16 empty] | & Time Boxes | [28 empty] | Dangerous
Business Objectives
& Feature Sets
Burndowns
Current &
Previous
Summary & Forecast
The available-to-promise and brochure display bugs have been prioritized and now occupy the backlog for our final sprint. The patches provided by our software vendor coupled with experienced efforts by internal team have remedied purchased software sluggishned. Legacy system interfaces continue to plague us although adequate for current operations. We are planning a new project to address delayed fixes. The new functionality and add communication capacity has more than offset early client irritation. Some features were delayed We met budget and timing.

## Data
| 0 |  | 4 | 4 | 5
Overall Status
Actual | 3 | 7 | 11 | 16 | 20 | 22 | 26 | 31 | 35 | 38 | 40 | 44 | 45 | 53 | 57 | 62 | 68 | 69 | 74 | 77 | 82
Adequate | 3 | 7 | 11 | 15 | 19 | 23 | 27 | 31 | 35 | 39 | 43 | 47 | 51 | 55 | 59 | 63 | 67 | 71 | 75 | 79 | 83
Ideal | 3 | 8 | 13 | 18 | 23 | 28 | 33 | 38 | 43 | 48 | 53 | 58 | 63 | 68 | 73 | 78 | 83 | 88 | 93 | 98 | 103
Sprint10
Days | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | 0
Points | 80 | 72 | 64 | 56 | 48 | 40 | 40 | 32 | 24 | 16 | 8 | 8
Sprint11
Days | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | 0
Points | 80 | 77 | 62 | 55 | 47 | 44 | 40 | 32 | 24 | 16 | 8 | 8

## Instructions
Instructions
1) Product Owner: name of product owner
2) Project name of project or project code (project name is preferred)
3) Report Date: should be filled with week number
4) Project Duration: project start date and end date.
5) Scrum Master: name of scrum master
6) Vision: Project general objectives
7) Business Objectives: business motivations of this project, how do we help customers in solving their business demands? Business objectives should be associated with Major Tasks /Deliverables and Risks, Qualitative, Other Metrics.
8) Feature Sets: the main features of product/system developed by project. The products features should be associated with Major Tasks /Deliverables and Risks, Qualitative, Other Metrics.
9) Releases and Sprints: the main releases (deliverables) with sprints defined for each of them
10) Schedule: based on scrum sprint cycle, 1-4 weeks for each sprint.(time-boxed)
11) Risks, Qualitative, Other Metrics: main risks, qualitative and metrics specified for project only, should be tracked every week. The list should give the new and on-going risks higher priority to be shown.
12) Key Metrics: standard project metrics which is clearly measured in numbers and in week. Please refer to sheet Key Metrics criteria for detailed information
13) 7-Key Status: 7-key appraisals of the projects. There should be question lists to be directed for the status. It's recommend to go through and answer the question list only once every release, typically, the first sprint of that release. Then, the status should be checked with comparisons to the previous ones (unnecessarily to answers the question list for sprint that not the first sprint of the releases).
14) Sprint Dates and Time Boxes: the week number associated with sprint releases
15) Burndowns Current & Previous: burn down charts for 2 latest sprints. Additionally, there is also an overall Burn-up chart of the project.
16) Summary and Forecast: the project summary, highlights and forecast, fully assessed by PM.
17) Red "Straight Line": the line to present the current week of the report.
18) "White dot" and "black dot": the dots are for tracking associations of two items. If it is white dot, the associated link is planned and does not happen or complete yet. If it is the black one, the associated link is completed or happened. Obviously, there are some spaces without any dots for presenting no association link at all.
19) # People on the Development Team: the number of human resources assigned to development team only, excluding PO and SM.
20) Average Weekly Team Velocity: velocity number measured at a weekly basis.
21) Backlog, Adequate, Worrisome, Dangerous: the color of status which are "Green", "Yellow", "Red" or "Grey", depending on items values and the criteria, the colors will be decided accordingly.

## Key Metrics Criteria
FSU1 Norms of Key Metrics Measurement (Agile Project)
# | Metrics | Unit | Norm
1 | Leakage | Weighted Defect/Man month | 0.34
2 | Defect rate | Weighted Defect/Man month | 25
3 | Timeliness | % | 95
4 | Effort Efficiency | % | 93
5 | Correction Cost | % | 6
6 | Productivity | % | Expected actual data is 100%
Color Definition of Key Metrics
# | Color | Criteria |  | Example (development project)
1 | Green | Deviation <10% |  | Defect rate: N: 25 Wdef/MM, A: 27 Wdef/MM, Deviation: (27-25)/25 = 0.08 (8%)
2 | Yellow | Deviation > 10% and <20% |  | EE: A: 81%, N: 93%, Deviation: (93%-81%)/93% ~ 0.13%
3 | Red | Deviation > 20% |  | Correction Cost: A = 9, N = 6, Deviation: (9-6)/6 = 50%
Legend
Deviation% = (actual value - norm) / norm
AV: Actual Value
N: Value set by Norm
Note on E9: Pham Dang Hung (FSU1.BU36): Currently, QA does not have full measurement to have norm of this key metric, to be defined soon.