## Report
LOGO | [5 empty] | Project Manager: Clark Campbell | [7 empty] | Project Name: Award Distribution Center (ADC) | [14 empty] | Report Date: March 2
[14 empty] | Project Duration: |  |  | Jan 01 13 - Mar 29 13
Project Objective: Consolidate Warehouses; Automate Storage and Retrieval; Reengineer Assembly, Packaging, Shipping of Recognition Awards
Business Objectives |  |  |  |  | Feature Sets | [5 empty] | Major Tasks / Deliverables | [6 empty] | Schedule
˜ |  |  |  |  | ˜ |  |  |  |  | 1 | Award Contracts to Architects and Contractors | [6 empty] | ˜ | ˜
˜ |  |  |  |  | ˜ |  |  |  |  | 2 | Dispose of Inventory, Raze Structure and Prepare Site | [6 empty] | ˜ | ˜ | ˜
|  |  | ˜ |  | ˜ |  |  |  |  | 3 | Design System Software | [6 empty] | ˜ | ˜ | ˜ | ˜
|  |  | ˜ |  | ˜ | ˜ |  | ˜ |  | 4 | Determine Computer Hardware Specifications | [6 empty] | ˜ | ˜ | ˜ | ˜ | ˜ | ˜
|  |  |  | ˜ | ˜ |  |  |  |  | 5 | Redesign Workstations | [10 empty] | ˜ | ˜ | ˜ | ˜ | ˜
˜ |  |  |  |  | ˜ |  |  |  |  | 6 | Plan and Complete the Parking and Landscaping | [7 empty] | ˜ | ˜ | ˜ | ˜
˜ | ˜ | ˜ |  |  |  | ™ |  | ˜ | ™ | 7 | Footings and Foundations | [9 empty] | ˜ | ˜ | ˜
˜ | ˜ | ˜ |  |  |  | ™ | ˜ |  |  | 8 | Columns and Beams | [10 empty] | ˜ | ˜ | ˜ | ˜
˜ | [5 empty] | ˜ |  |  |  | 9 | Roff Cap | [10 empty] | ˜ | ˜ | ˜ | ˜ | ˜
˜ | [6 empty] | ™ |  | ˜ | 10 | Main Floor | [12 empty] | ˜ | ˜ | ˜ | ˜
˜ | ˜ | [5 empty] | ™ |  |  | 11 | Exterior and Glass | [12 empty] | ˜ | ˜ | ˜
| ˜ |  | ˜ |  | ˜ |  |  |  |  | 12 | Install Computer Hardware | [12 empty] | ˜ | ˜ | ˜
| ™ |  | ˜ |  |  |  |  | ˜ |  | 13 | Assemble and Install Storage Racking | [12 empty] | ˜ | ˜
| ˜ |  | ˜ |  |  | ˜ |  |  |  | 14 | Mount and Align Automated Cranes | [12 empty] | ˜ | ˜ | ˜
| ˜ |  | ˜ |  |  |  | ™ |  |  | 15 | Install and Connect Conveyors between Racking and Workstations | [13 empty] | ˜ | ˜ | ™
|  | ™ | ™ |  |  |  | ™ |  |  | 16 | Program, Test and Install Software | [6 empty] | ˜ | ˜ | ˜ | ˜ | ˜ | ˜ | ˜ | ˜ | ™ | ™ | ™ | ™ | ™
| ™ |  |  | ˜ |  |  | ™ |  |  | 17 | Train Staffs on New Systems, Processes and Performance Goals | [12 empty] | ˜ | ˜ | ™ | ™ |  | ™ | ™
˜ |  | ˜ |  |  |  |  | ™ |  |  | 18 | Mezzanine Floor | [6 empty] | ˜ | ˜ | ˜ | ˜ | ˜ | ˜ | ˜ | ˜ | ˜ | ™ | ™ | ™
|  | ˜ |  | ˜ | ˜ |  |  |  |  | 19 | Install Workstation and New Furnishings | [16 empty] | ™
|  |  |  | ˜ |  |  | ˜ |  |  | 20 | Move Staff into ADC | [16 empty] | ™
|  |  |  | ˜ |  |  | ™ |  |  | 21 | Transfer Inventory | [16 empty] | ™ | ™ | ™
|  | ˜ |  | ˜ |  |  | ™ |  |  | 22 | Install Workstation and New Furnishings | [16 empty] | ™
|  |  |  | ˜ | ˜ |  | ™ |  |  | 23 | Move Staff into ADC | [16 empty] | ™
|  |  |  | ˜ | ˜ |  | ˜ |  |  | 24 | Transfer Inventory | [16 empty] | ™ | ™ | ™
|  | ˜ |  | ˜ | ™ |  |  |  |  | 25 | Install Workstation and New Furnishings | [16 empty] | ™
|  |  |  | ˜ | ™ |  | ™ | ˜ |  | 26 | Move Staff into ADC | [16 empty] | ™
|  |  |  | ˜ | ™ |  | ™ |  |  | 27 | Transfer Inventory | [16 empty] | ™ | ™ | ™
|  |  |  | ™ | ™ |  |  |  |  | 28 | Plan Staffing Requirements | [7 empty] | ˜ | ˜ |  | ˜ |  |  |  | ˜ | ˜ | ™ | ™ | ™
Risks, Qualitative, Other Metrics
|  |  | ˜ |  | ˜ | ˜ | ˜ |  |  | 1 | Performance of Software Developed Internally
| ™ | ™ | ™ |  |  |  | ™ |  |  | 2 | Performance of Software Developed Externally
| ˜ | ˜ | ˜ |  |  |  | ™ |  |  | 3 | Performance of Fully Integrated System, Machines and Processes
™ |  |  | ™ | ™ |  |  | ˜ | ˜ |  | 4 | Retain Subcontractors Versus Large Competing Construction Project?
™ |  |  | ™ | ™ |  |  | ˜ | ˜ |  | 5 | Will the Building, Systems, and People be Ready for ON-TIME Go-live?
Key Metrics
Earn community appreciation | Inspire customers for a better product | Building Complete | Systems Operational | People Deployed | Upgrade Order Design Features | Upgrade Pricing Features | Upgrade Available-to-Promise Features | Upgrade Brochure Display Features | Upgrade Invoicing Features | A | Leakage (Wdef/MM) | [6 empty] | 0.34 | 0.3 | 0.29 | 0.29 | 0.31 | 0.37 | 0.41 | 0.38 | 0.38
[10 empty] | B | Defect Rate (Wdef/MM) | [6 empty] | 15 | 17 | 20 | 20 | 21 | 22 | 27.6 | 28 | 31
[10 empty] | C | Timeliness (%) | [6 empty] | 100% | 99% | 98% | 97% | 96% | 95% | 95% | 77% | 50%
[10 empty] | D | Effort Efficiency (%) | [6 empty] | 100% | 85% | 85% | 99% | 82% | 82% | 81% | 81% | 81%
[10 empty] | E | Correction Cost (%) | [6 empty] | 5% | 6.5% | 6.4% | 6% | 6.8% | 5% | 5.1% | 5.1% | 7.2%
[10 empty] | F | Productivity (%) | [6 empty] | 100% | 86% | 87% | 95% | 85% | 99% | 98% | 96% | 77%
7-Key Status
[10 empty] | A | Stake Holders
[10 empty] | B | Business Benefits
[10 empty] | C | Work Schedule
[10 empty] | D | Scope
[10 empty] | E | Team
[10 empty] | F | Risk
[10 empty] | G | Organizational Benefits
[10 empty] | Internal People assigned to the Project: | [7 empty] | 16 | 18 | 16 | 16 | 17 | 16 | 16 | 16 | 18 | 18 | 18 | 18 | 18
[18 empty] | Week 01 | Week 02 | Week 03 | Week 04 | Week 05 | Week 06 | Week 07 | Week 08 | Week 09 | Week 10 | Week 11 | Week 12 | Week 13
Major Tasks, Risks, Key Metrics
& 7-Key Status
Report Dates
[27 empty] | EV = |  | 55000
[27 empty] | PV = |  | 75000
[27 empty] | AC= | BAC= | 40000
[11 empty] | Business Objectives |  |  |  | Earned Value |  |  | Week 10: BAC =; Week 11: AC =; Week 12: 150000
[11 empty] | & Feature Sets |  |  |  |  | Management |  | Week 10: CV =; Week 11: CV =; Week 12: 15000
[27 empty] | SV = |  | -20000
[27 empty] | CPI = |  | 1.375
[13 empty] | Summary & Forecast |  |  |  |  | Week 10: SPI =; Week 12: 0.73333
[27 empty] | ETC= | ETC= | 94214.876
[27 empty] | EAC= | EAC= | 134214.876
[27 empty] | VAC = |  | 15785.124
[27 empty] | TCPI = | TCPI = | 0.86364
We are planning to bring the ADC operational by year-end. System costs overruns are more than offset by savings secured in the construction process. Half of the constructions saving will be paid out as incentive bonuses to the subcontractors. System test have been completed without critical issues. Our team is confident that the remaining software issue will be resolved and adequate for go-live. Refinement will still be required. People have been trained, and are anxious to begin full operation.
|  |  | Complete |  |  | ˜
|  |  | Incomplete |  |  | ™
Adequate
Worrisome
Dangerous

## Data
Person-day/Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
PV | 100 | 120 | 150 | 200 | 300 | 400 | 450 | 600 | 750 | 950 | 1200 | 1500
EV | 150 | 200 | 240 | 270 | 280 | 350 | 400 | 450 | 550
AC | 120 | 170 | 200 | 220 | 260 | 300 | 320 | 350 | 400

## Instructions
Instructions
1) Project Manager: name of project manager
2) Project Name: name of project or project code (project name is preferred)
3) Report Date: should be filled with Month and Date.
4) Project Duration: project start date and end date.
5) Project Objective: project general objective.
6) Business Objectives: business motivations of this project, how do we help customers in solving their business demands? Business objectives should be associated with Major Tasks /Deliverables and Risks, Qualitative, Other Metrics.
7) Feature Sets: the main features of product/system developed by project. The products features should be associated with Major Tasks /Deliverables and Risks, Qualitative, Other Metrics.
8) Major Tasks / Deliverables: the major task or the content of deliverables.
9) Schedule: The planed schedule of the project, divided by week. Recommended to have the number of week fitted in one-page print. If there are so many weeks, the earliest (obsolete) date should be removed.
10) Risks, Qualitative, Other Metrics: main risks, qualitative and metrics specified for project only, should be tracked every week. The list should give the new and on-going risks higher priority to be shown.
11) Key Metrics: standard project metrics which are clearly measured in numbers. Please refer to sheet Key Metrics criteria for detailed information
12) 7-Key Status: 7-key appraisals of the projects. There should be question lists to be directed for the status. It's recommend to go through and answer the question list only once a month, typically, the first week of the month. In a month, the status should be checked with comparisons to the previous ones (unnecessarily to answers the question list for the weeks that not the first week of the month).
13) Report Dates: divided by week as it is for weekly report.
14) Earned Value Management (EVM): for EVM calculation for project status, calculated with project effort (person-day). The outputs are already formularized.
15) Summary and Forecast: the project summary, highlights and forecast, fully assessed by PM.
16) Red "Straight Line": the line to present the current week of the report.
17) "White dot" and "black dot": the dots are for tracking associations of two items. If it is white dot, the associated link is planned and does not happen or complete yet. If it is the black one, the associated link is completed or happened. Obviously, there are some spaces without any dots for present no association link at all.
18) Internal People assigned to the project: the number of human resources assigned to the project, tracked every report week.
19) Adequate, Worrisome, Dangerous: the color of status which are "Green", "Yellow" and "Red", depending on items values and the criteria, the colors will be decided accordingly.

## Key Metrics Criteria
FSU1 Norms of Key Metrics Measurement (Non-Agile project)
# | Metrics | Unit | Development | Maintenance | Test
1 | Leakage | Weighted Defect/Man month | 0.34 | 0.2 | 0
2 | Defect rate | Weighted Defect/Man month | 25 | 17 | 6
3 | Timeliness | % | 95 | 98 | 98
4 | Effort Efficiency | % | 93 | 95 | 100
5 | Correction Cost | % | 6 | 4 | 1
6 | Productivity | % | Expected actual data is 100%
Color Definition of Key Metrics
# | Color | Criteria |  | Example (development project)
1 | Green | Deviation <10% |  | Defect rate: N: 25 Wdef/MM, A: 27 Wdef/MM, Deviation: (27-25)/25 = 0.08 (8%)
2 | Yellow | Deviation > 10% and <20% |  | EE: A: 81%, N: 93%, Deviation: (93%-81%)/93% ~ 0.13%
3 | Red | Deviation > 20% |  | Correction Cost: A = 9, N = 6, Deviation: (9-6)/6 = 50%
Legend
Deviation% = (actual value - norm) / norm
AV: Actual Value
N: Value set by Norm
Note on E9: Pham Dang Hung (FSU1.BU36): Currently, QA does not have full measurement to have norm of this key metric, to be defined soon.